## Product Backlog
Planned Sprint | Actual Sprint | Task ID | Epic/Module | Description | Assigned To | Dependency | Status
1 | 1 | T1 | Data Ingestion | Scraped competitor product pricing daily and cleaned the data |  | - | Completed
2 | 2 | T2 | Training ML Model | Trained the model to predict future trends with the cleaned data |  | T1 | Completed
3 | 3 | T3 | Sentiment Analysis | Performed sentiment analysis on customer reviews |  | T1 | Completed
4 | 4 | T4 | Dashboard UI | Build interactive competitor insights dashboard |  | T2 | Completed
5 | 5 | T5 | Notification Alerts | Send alerts when competitor drops price |  | T3 | Completed

## Sprint Backlog
Sprint | Tasks Description | Start Date | Completion Date | Team Member | Activity | Status | Estimated Efforts(in Hrs) 28Hrs
1 | Scraped competitor product pricing daily and cleaned the data |  |  |  | Data engineering | Completed | 4
2 | Trained the model to predict future trends with the cleaned data |  |  |  | Coding | Completed | 7
3 | Performed sentiment analysis on customer reviews |  |  |  | Coding | Completed | 5
4 | Build interactive competitor insights dashboard |  |  |  | Design | Completed | 9
5 | Send alerts when competitor drops price |  |  |  | Coding | Completed | 3

## Retrospective
Sl# | Sprint | Start Date | Stop Date | Start Doing | Stop Doing | Continue Doing | Action Items
1 | 1 |  |  | Automated competitor data scraping | Manual competitor data checks | Data cleanup | Add monitoring for scraping failures
2 | 2 |  |  | Data ingestion & preprocessing | Manual validation of ingested data | Data cleanup and pipeline checks | Automate ingestion validation scripts
3 | 3 |  |  | ML prediction & sentiment integration | UI performance issues | Optimized UI and caching | Create stable scraping framework
4 | 4 |  |  | Early UI review sessions | Fixing issues late in sprint | Continuous integration & testing | Introduce design review checkpoints
5 | 5 |  |  | Proactive dependency planning | Delayed code merges | Optimized UI & caching | Finalize alert system and enhance dashboard